## Sheet2
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25
WP1 Research & Planning | W5: ▲M1
WP2 Dataset & Model Training | W9: ▲M2
WP3 Android Development | W15: ▲M3
WP4 Backend & Dashboard | bar: W10 to W14
WP5 Integration & Testing | W19: ▲M4/M5
WP6 Report Writing | W25: ▲M6
Legend | W3: Milestones
WP1 Research & Planning | W3: M1: W5 — Research & Planning complete
WP2 Dataset & Model Training | W3: M2: W9 — Dataset & Model Training complete
WP3 Android Development | W3: M3: W15 — Android Development complete
WP4 Backend & Dashboard | W3: M4: W19 — Integration & Testing phase 1
WP5 Integration & Testing | W3: M5: W19 — Integration & Testing complete
WP6 Report Writing | W3: M6: W25 — Report Writing complete
▲ = Project Milestone